## Tasks
Web-based Network Load Balancing System
Task | SubTask | Estimate | Start Date
Scheduling Algorithm | Code least connected | 4
| Code weighted | 4
| Code ip-hash | 4
| Code sticky round-robin | 4
Logging | Code tracing system | 6
Reporting | Code reporting system | 6
Health Monitoring Service | Code health monitoring service | 6
| Connect health monitoring service | 4
| Code health based scheduling service | 4
Database | Define database | 4
| Create database and entity classes | 4
| Create database interfaces | 4
Console Front-end | Create front-end templates | 10
| Create front-end js classes | 10
| Integrate front-end with backend | 10
84